CenturyLink OSS Release Calendar

ASR

ASR GATEWAY/EASE Release 5.0/ASOG 57

Draft Technical Specifications Issued July 6, 2018

Comment cycle starts July 6, 2018

Comment cycle ends July 24, 2018

Final Technical Specifications Issued August 3, 2018

Testing Available August 18, 2018

Draft ASR EASE GUI Documentation Issued August 20, 2018

Comment cycle starts August 20, 2018

Comment cycle ends August 23, 2018

Final ASR EASE GUI Documentation Issued August 27, 2018

Release Production Date September 17, 2018

ASR GATEWAY/EASE Point Release 5.1

Custom Business Rules Notification Issued October 12, 2018

Comment cycle starts October 12, 2018

Comment cycle ends October 22, 2018

Final Custom Business Rules Notification Issued, if required October 26, 2018

Release Production Date November 12, 2018

ASR GATEWAY/EASE Point Release 5.2

Custom Business Rules Notification Issued December 21, 2018

Comment cycle starts December 21, 2018

Comment cycle ends December 31, 2018

Final Custom Business Rules Notification Issued, if required January 4, 2019

Release Production Date January 21, 2019

ASR GATEWAY/EASE Release 6.0/ASOG 58

Draft Technical Specifications Issued January 4, 2019

Comment cycle starts January 4, 2019

Comment cycle ends January 22, 2019

Final Technical Specifications Issued February 1, 2019

Testing Available February 16, 2019

Draft ASR EASE GUI Documentation Issued February 18, 2019

Comment cycle starts February 18, 2019

Comment cycle ends February 21, 2019

Final ASR EASE GUI Documentation Issued February 25, 2019

Release Production Date March 18, 2019

ASR GATEWAY/EASE Release 7.0/ASOG 59

Draft Technical Specifications Issued July 12, 2019

Comment cycle starts July 12, 2019

Comment cycle ends July 30, 2019

Final Technical Specifications Issued August 9, 2019

Testing Available August 24, 2019

Draft ASR EASE GUI Documentation Issued August 26, 2019

Comment cycle starts August 26, 2019

Comment cycle ends August 29, 2019

Final ASR EASE GUI Documentation Issued September 2, 2019

Release Production Date September 23, 2019

LSR

IMA

IMA 40.0 RELEASE

Commitment – at CMP Meeting November 16, 2016

Release Production Date April 3, 2017

Release Sunset TBD

IMA 41.0 RELEASE POTENTIALLY 1st Quarter 2019 Release*

CMP CR Submission Cutoff

Prioritization – at CMP Meeting

Packaging – at CMP Meeting

Commitment – at CMP Meeting

Draft XML Technical Specifications Issued

Comment cycle starts

Comment cycle ends

Final XML Technical Specifications Issued

SATE Available

Draft GUI Release Notes Issued

Comment cycle starts

Comment cycle ends

Final GUI Release Notes Issued

Release Production Date

Release Sunset

*REVISED DATE

IMA Retirement (see Milestones Timeline below for LSR Project Consolidation Plan)

Initial IMA Retirement Notification Issued – App to APP and GUI January 4, 2016

Planned IMA Production Date Retirement – Eastern Region REVISED No earlier than First Quarter 2020

*REVISED DATE NOTE: All existing accounts for the Eastern region are converted via a flash cut. All ongoing LSRs will be processed through EASE and all subsequent bills will be generated from Ensemble.

EASE Introduction (see Milestones Timeline below for LSR Project Consolidation Plan)

Initial EASE Release Notification - LSR App to App and GUI January 4, 2016

Planned EASE Production Date – LSR – Eastern Region REVISED No earlier than First Quarter 2020

*REVISED DATE NOTE: All existing accounts for the Eastern region are converted via a flash cut. All ongoing LSRs will be processed through EASE and all subsequent bills will be generated from Ensemble.

LSR PROJECT CONSOLIDATION PLAN

Consolidation completion for the Eastern region is TO BE DETERMINED*.  The target dates for the Western region and Central region are being reevaluated at this time.  CenturyLink will comply with all applicable Merger Requirements, including use of the CMP process.

The following table shows a list of milestones that impact the Consolidation Plan. CenturyLink will communicate updated milestone dates per the CMP process.

= A milestone, established by the Merger Requirements, that alters the established CMP milestones schedule.

| Consolidation Plan Milestone | Date |
| --- | --- |
| CMP CR Issuance: SCR110415-1, SCR110415-2, SCR110415-3, SCR110415-4 These can be found at: http://www.centurylink.com/wholesale/cmp/cr/crnumber_system_index.html | 11/4/15 |
| CR Presentation at CMP Meeting | 11/18/15 |
| LSR Consolidation Plan due | 1/4/16 |
| Initial Release Notification (for SCR110415-1 and SCR110415-2) | 1/4/16 |
| Initial Retirement Notice (for SCR110415-3 and SCR110415-4) | 1/4/16 |
| LSR Consolidation Plan Review Meeting REVISED | 1/27/16 |
| Extended Customer Comment Window for Initial Release Notification, Initial Retirement Notice and Consolidation Plan REVISED | 2/11/16 |
| CenturyLink issues response to CLEC comments and Final Retirement Notice, including the Final version of the LSR Consolidation Plan REVISED | 3/7/16 |
| 3rd Party Facilitator Selected NOTE: The CenturyLink 3rd Party Facilitator recommendation was provided during the March 2016 CMP monthly meeting. | 3/16/16 |
| Draft Interface Tech Specs | 8/12/16* |
| Comment cycle Starts | 8/12/16* |
| Tech Specs Walk-through(s) | 8/23/16* and 9/7/16 |
| CLEC Comments Ends for Interface Tech Specs | 9/16/16* |
| Final Interface Tech Specs | 9/30/16* |
| DATES REVISED BELOW TO SHOW TO BE DETERMINED (TBD) UNTIL THE RELEASE TO PRODUCTION DATE IS FINALIZED |
| L&P Volume Testing | TBD |
| (New) GUI Initial Release notice | TBD |
| (New) GUI Draft Release notes | TBD |
| Product Process Notification associated with Level 2 OSS changes | TBD |
| CLEC comments due on (New) GUI Release Notes | TBD |
| CLEC comments due on Level 2 OSS Product Process changes | TBD |
| Training available | TBD |
| GUI Final Release Notice | TBD |
| Final Notice For Level 2 OSS Product/Process Changes | TBD |
| Customer Testing Begins with LSR Consolidation Functionality (120 Days) | TBD |
| Customer Testing Ends | TBD |
| Customer Go/No Go Vote | TBD |
| Eastern Region Release to Production REVISED | No earlier than First Quarter 2020 |

* REVISED DATE

File Transfer Protocol

CPID/QPID Retirement NOTE: CPID/QPID is not a system application. It is a File Transfer interface.

Initial CPID/QPID Retirement Notification Issued February 23, 2018

Comment cycle starts February 23, 2018

Comment cycle ends March 9, 2018

Final CPID/QPID Retirement Notification Issued April 6, 2018

Planned CPID/QPID Production Retirement Date April 1, 2019*

* REVISED DATE

BILLING OUTPUT

May include any/all of the following: ASCII, Paper, EDI, BOS BDT, internet downloadable files (Billmate, BOS BDT or a print image of bill).

CABS Billing Output Specifications (BOS)    March 2019 Release

Draft Technical Specifications Issued November 30, 2018

Comment cycle starts November 30, 2018

CenturyLink/CLEC Walkthrough December 12, 2018 (following the Monthly CMP Meeting)

Comment cycle ends December 18, 2018

Final Technical Specifications Issued December 28, 2018

Testing Available January 30, 2019

Release Production Date March 1, 2019

Ensemble Introduction - Eastern Region (see Milestones Timeline below for LSR Project Consolidation Plan)

Initial Ensemble Release Notification Issued January 4, 2016

Planned Ensemble Production Date – Eastern Region REVISED No earlier than First Quarter 2020

* REVISED DATE NOTE: All existing Eastern accounts are converted via a flash cut. All ongoing LSRs will be processed through EASE and all subsequent bills will be generated from Ensemble

CRIS Retirement - Eastern Region (see Milestones Timeline below for LSR Project Consolidation Plan)

Initial CRIS Retirement Notification Issued January 4, 2016

Planned CRIS Production Retirement – Eastern Region REVISED No earlier than First Quarter 2020

* REVISED DATE NOTE: All existing Eastern accounts are converted via a flash cut. All ongoing LSRs will be processed through EASE and all subsequent bills will be generated from Ensemble.

Currently there are no planned Releases for the following Systems:

# CEMR-MTG                                                    IMA

# DLIS				          Loss and Completions

# Billing				          MTG

# The CenturyLink OSS Release Calendar includes tasks from the CLEC-CenturyLink Wholesale Change Management Process Document available at http://www.centurylink.com/wholesale/cmp/index.html.  Proposed release dates provided are targets. Changes may occur during an OSS release lifecycle that could impact target dates. If target dates are updated, the CenturyLink OSS Release Calendar will be updated to reflect the revised target release dates.

Issued By		CenturyLink Wholesale Change Management Process (CMP)

Business Unit		CenturyLink Wholesale Program

Effective Date		9/14/18

Publication Location	http://www.centurylink.com/wholesale/cmp/teammeetings.html