CenturyLink OSS Release Calendar

ASR

ASR GATEWAY/EASE New API – NOTE: These dates are to begin testing with impacted customers.

Draft Technical Specifications Issued October 19, 2018

Comment cycle starts October 19, 2018

Comment cycle ends October 27, 2018

Final Technical Specifications Issued November 6, 2018

Testing Available December 1, 2018

Release Production Date December 31, 2018 Full implementation in Production is planned for November 2019.

ASR GATEWAY/EASE Release 7.0/ASOG 59

Draft Technical Specifications Issued July 12, 2019

Comment cycle starts July 12, 2019

Comment cycle ends July 30, 2019

Final Technical Specifications Issued August 9, 2019

Testing Available August 24, 2019

Draft ASR EASE GUI Documentation Issued August 26, 2019

Comment cycle starts August 26, 2019

Comment cycle ends August 29, 2019

Final ASR EASE GUI Documentation Issued September 2, 2019

Release Production Date September 23, 2019

ASR GATEWAY/EASE Point Release 7.1

Custom Business Rules Notification Issued October 18, 2019

Comment cycle starts October 18, 2019

Comment cycle ends October 28, 2019

Final Custom Business Rules Notification Issued, if required November 1, 2019

Release Production Date November 18, 2019

ASR GATEWAY/EASE Point Release 7.2

Custom Business Rules Notification Issued December 20, 2019

Comment cycle starts December 20, 2019

Comment cycle ends December 30, 2019

Final Custom Business Rules Notification Issued, if required January 3, 2020

Release Production Date January 20, 2020

ASR GATEWAY/EASE Release 7.0/ASOG 60

Draft Technical Specifications Issued January 10, 2020

Comment cycle starts January 10, 2020

Comment cycle ends January 28, 2020

Final Technical Specifications Issued February 7, 2020

Testing Available February 22, 2020

Draft ASR EASE GUI Documentation Issued February 24, 2020

Comment cycle starts February 24, 2020

Comment cycle ends February 27, 2020

Final ASR EASE GUI Documentation Issued March 2, 2020

Release Production Date March 23, 2020

ASR GATEWAY/EASE Release 8.0/ASOG 61

Draft Technical Specifications Issued July 10, 2020

Comment cycle starts July 10, 2020

Comment cycle ends July 28, 2020

Final Technical Specifications Issued August 7, 2020

Testing Available August 22, 2020

Draft ASR EASE GUI Documentation Issued August 24, 2020

Comment cycle starts August 24, 2019

Comment cycle ends August 27, 2020

Final ASR EASE GUI Documentation Issued August 31, 2020

Release Production Date September 21, 2020

LSR

IMA

IMA 40.0 RELEASE

Commitment – at CMP Meeting November 16, 2016

Release Production Date April 3, 2017

Release Sunset TBD

IMA 41.0 RELEASE DATES TBD

CMP CR Submission Cutoff

Prioritization – at CMP Meeting

Packaging – at CMP Meeting

Commitment – at CMP Meeting

Draft XML Technical Specifications Issued

Comment cycle starts

Comment cycle ends

Final XML Technical Specifications Issued

SATE Available

Draft GUI Release Notes Issued

Comment cycle starts

Comment cycle ends

Final GUI Release Notes Issued

Release Production Date

Release Sunset

File Transfer Protocol

CPID/QPID Retirement NOTE: CPID/QPID is not a system application. It is a File Transfer interface.

Initial CPID/QPID Retirement Notification Issued February 23, 2018

Comment cycle starts February 23, 2018

Comment cycle ends March 9, 2018

Final CPID/QPID Retirement Notification Issued April 6, 2018

Planned CPID/QPID Production Retirement Date December 31, 2019*

* REVISED DATE

BILLING OUTPUT

May include any/all of the following: ASCII, Paper, EDI, BOS BDT, internet downloadable files (Billmate, BOS BDT or a print image of bill).

Currently there are no planned Releases for the following Systems:

# Billing 			 	CEMR-MTG

# DLIS		  	               IMA

# Loss and Completions                           MTG

# The CenturyLink OSS Release Calendar includes tasks from the CLEC-CenturyLink Wholesale Change Management Process Document available at http://www.centurylink.com/wholesale/cmp/index.html.  Proposed release dates provided are targets. Changes may occur during an OSS release lifecycle that could impact target dates. If target dates are updated, the CenturyLink OSS Release Calendar will be updated to reflect the revised target release dates.

Issued By		CenturyLink Wholesale Change Management Process (CMP)

Business Unit		CenturyLink Wholesale Program

Effective Date		04/12/19

Publication Location	http://www.centurylink.com/wholesale/cmp/teammeetings.html