| **Consolidation Plan Milestone** | **Date** |
| --- | --- |
| CMP CR Issuance: These can be found at: <http://www.centurylink.com/wholesale/cmp/cr/crnumber_system_index.html>  | 12/2/19  |
| CR Presentation at CMP Meeting | 12/18/19 |
| Local Service Request Consolidation Plan due  | 1/13/2020 |
| Local Service Request Consolidation Plan Review Meeting | 1/22/2020 |
| Extended Customer Comment Window for Initial Release Notification, Initial Retirement Notice and Consolidation Plan  | **2/5/2020**  |
| CenturyLink issues response to CLEC comments including the Final version of the Local Service Request Consolidation Plan | **2/26/2020**  |
| Draft Interface Tech Specs  | 3/18/2020  |
| Tech Specs Walk-through |  3/25/2020 – 4/15/2020 |
| CLEC Comments for Interface Tech Specs | 4/30/2020   |
| Final Interface Tech Specs | 5/15/2020  |
| Product Process Notification associated with Level 2 OSS changes | 5/15/2020  |
| CLEC comments due on (New) GUI Release Notes | 6/5/2020  |
| CLEC comments due on Level 2 OSS Product Process changes |  6/5/2020 |
| Training available | 6/5/2020  |
| GUI Final Release Notice | 6/19/2020  |
| Final Notice For Level 2 OSS Product/Process Changes | 6/19/2020  |
| Customer Testing Begins with Local Service Request Consolidation Functionality (120 Days) | 6/5/2020  |
| Customer Testing Ends | 1/22/2021 |
| Customer Go/No Go Vote  | 1/22/2021  |
| Migration to EASE Production | 1/23/2021 |
| Customer Implementation to Production Environment Live on | 1/25/2021 |